Virtual Care PDSA Onboarding Checklist

| Task | Expected Timeline | Date Completed | Additional Comments |
| --- | --- | --- | --- |
| Complete Expression of Interest application and Receive iPad to support Virtual Care practices across the home. Note: Some homes may have to have their iPad processed by their IT department. | July |  |  |
| Decide which technology platform would best fit with the current practices in your home: - For homes that use Point Click Care or Med-E-Care: Think Research’s VirtualCare platform may be the best option - For homes that do not use either EHR: OTN through your primary care providers may be the best option | Within 1-2 weeks of receiving a tablet |  |  |
| *For Think Research Users*: Please register for Think Research’s LTC VirtualCare technology via this link: https://www.tfaforms.com/4820824​ | As soon as possible |  |  |
| *For OTN Users*: Obtain a list of your MD/NPs that support all of the residents in your home as well as their email addresses if possible, to submit to your NLOT/BSO nurse consultant. | As soon as possible |  |  |
| Establish training sessions with your home: - Think Research will contact homes to provide training sessions on their technology - OTN training can be coordinated with your NLOT/BSO nurse consultant and the eHealth Centre of Excellence | Within 2 weeks of receiving technology |  |  |
| Connect weekly with your NLOT/BSO nurse consultant to discuss any successes, concerns, your progression, and outcomes with the Virtual Care PDSA. - Please forward us a consistent date/time that we can hold standing telephone or OTN meetings (Note: Nurse Consultants will send the OTN invites) | Weekly (Create a standing meeting date/time) |  |  |
| Continue to use virtual care visits with your home’s providers to support resident care and avoid potential ED transfers! - Record this data in the data template provided by your NLOT/BSO Nurse Consultant | The end of each month data should be collected and sent to your nurse consultant. |  |  |

Nurse Consultant Contacts

Kayla Brooks	      kayla.brooks@sjhcg.ca	       226-218-1671

Nicole Guy	      nicole.guy@sjhcg.ca	       226-338-8670

Nasibah Dahi	      nasibah.dahi@sjhcg.ca	       226-979-1864

MaryAnn Glasier	      maryann.glasier@sjhcg,.ca    226-338-7370